## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
Week-2
Week2_Issue01 | Meeting | 2024-05-12 | Unable to schedule a meeting. | High | Project Manager | Project Manager | Open
Week2_Issue02 | Logo | 2024-05-14 | Unable to finalize logo among many options. | Medium | Developer | Team | Open
Week2_Issue03 | Template | 2024-05-14 | Unable to understand the templates given by professor. | Medium | Scribe | Scribe | Open
Week2_Issue04 | Installation | 2024-05-12 | Project manager was not able to setup the environment required for the project. | Low | Project Manager | Project Manager | Open
Week-3
Week3_Issue01 | Communication | 2024-05-20 | Miscommunication between team members leading to redundant work. | High | Project Manager | Team | Open
Week3_Issue02 | Documentation | 2024-05-22 | Missing documentation for key project components. | Medium | Project Manager | Scribe | Open
Week-4
Week4_Issue01 | Discussion | 2024-05-31 | Meeting Topic Discussion | Low | Scribe | Team | Open
Week4_Issue02 | Decision | 2024-06-01 | Deciding the Test Plan | High | Project Manager | Tester | Open
Week4_Issue03 | Completion | 2024-06-01 | Incomplete Project Plan | Medium | Project Manager | Project Manager | Open
Week-7
Week7_Issue01 | Installation | 2024-06-25 | Unable to install the application | Medium | Project Manager | Team | Open
Week7_Issue02 | Decision | 2024-06-26 | Deciding the Use Cases | High | Developer | Team | Open
Week-8
Week8_Issue01 | Decision | 2024-07-10 | Unable to understand the test case template | High | Tester | Team | Open
Week8_Issue02 | Communication | 2024-07-12 | Miscommunication for misleading work | Medium | Project Manager | Team | Open

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
Week-2
Week2_Issue01 | Issue_1 | Schedule a meeting after a day. | 2024-05-13 | Low | Project Manager | Solved
Week2_Issue02 | Issue_2 | Had a group discussion and got opinion of every members and then finalized the logo. | 2024-05-14 | Low | Team | Solved
Week2_Issue03 | Issue_3 | Had a discussions with peers. | 2024-05-14 | Low | Scribe | Solved
Week2_Issue04 | Issue_4 | Tried to setup environment with the help of team members. | 2024-05-13 | Low | Project Manager | Solved
Week-3
Week3_Issue01 | Issue_1 | Schedule regular sync-up meetings to ensure clear communication. | 2024-05-22 | Low | Project Manager | Solved
Week3_Issue02 | Issue_2 | Assigned a team member to create and maintain the missing documentation. | 2024-05-23 | Low | Scribe | Solved
Week-4
Week4_Issue01 | Issue_1 | Taken Decision from each and every time member | 2024-06-01 | Low | Scribe | Solved
Week4_Issue02 | Issue_2 | Had a discussion in the meeting and decided the testing plan | 2024-06-01 | Medium | Project Manager | Solved
Week4_Issue03 | Issue_3 | Assigned work among members and tried to cope-up with the work. | 2024-06-01 | Medium | Project Manager | Solved
Week-7
Week7_Issue01 | Issue_1 | Tried to solve by discussing with peers. | 2024-06-25 | Low | Project Manager | Solved
Week7_Issue02 | Issue_2 | Had a discussion with the team member | 2024-06-26 | Low | Scribe | Solved
Week-8
Week8_Issue01 | Issue_1 | Discussed with team members and decided the test case. | 2024-06-11 | Low | Project Manager | Solved
Week8_Issue02 | Issue_2 | Assigned work equally and completed with time. | 2024-06-13 | Low | Scribe | Solved

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
Week-2
Week2_Issue01 | 2024-05-13 | Finalized date and time for group meeting. | Low | Issue_1
Week2_Issue02 | 2024-05-14 | Pixel logo finalized. | Low | Issue_2
Week2_Issue03 | 2024-05-14 | Able to understand the templates with the help of peers. | Low | Issue_3
Week2_Issue04 | 2024-05-13 | setup environment in team member's system. | Low | Issue_4
Week-3
Week3_Issue01 | 2024-05-22 | Implemented daily stand-up meetings to improve coordination among team members. | Low | Issue_1
Week3_Issue02 | 2024-05-23 | Documentation completed | Low | Issue_2
Week-4
Week4_Issue01 | 2024-06-01 | Meeting done successfully | Low | Issue_1
Week4_Issue02 | 2024-06-01 | Test Plan Decided. | Low | Issue_2
Week4_Issue03 | 2024-06-01 | Created a project plan | Medium | Issue_3
Week-7
Week7_Issue01 | 2024-06-25 | Finally application installed successfully | Low | Issue_1
Week7_Issue02 | 2024-06-26 | Use Cases Completed. | Low | Issue_2
Week-8
Week8_Issue01 | 2024-07-13 | Completed the test cases. | Low | Issue_1
Week8_Issue01 | 2024-07-13 | All work completed before deadline | Low | Issue_2

## Team
INFO6068 | Capstone Project
Team Name: | Team Pixel
Members: | Rutvik Patel
Sakshi Modi
Parth Patel
Vijul Vyas