## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 99
| Number of testers | 1
| Test cycle duration | 3 days
Status for 08/01/2024 | Number of test cases planned | 33
| Number of test cases executed | 33
| Number of test cases executed overall | 33
| Number of defects encountered today | 4
| Number of defect encountered so far | 4
| Number of critical defects- still open | 4
Status for 08/02/2024 | Number of test cases planned | 33
| Number of test cases executed | 33
| Number of test cases executed overall | 66
| Number of defects encountered today | 3
| Number of defect encountered so far | 7
| Number of critical defects- still open | 7
Status for 08/03/2024 | Number of test cases planned | 33
| Number of test cases executed | 33
| Number of test cases executed overall | 99
| Number of defects encountered today | 0
| Number of defect encountered so far | 7
| Number of critical defects- still open | 7
Overall status | Number of test cases planned | 99
| Number of test cases executed | 99
| Pass Percentage of the defects | 14.29%
| Defects density on 08/01/2024 | 0.12121
| Defects density on 08/02/2024 | 0.090909
| Defects density on 08/03/2024 | 0
| Defect density average | 0.21212 | Per day
| Defect average | 2.3333 | Per day
| Critical defects percentage | 100%

## Invalid Test Cases Execution
Module | Test Case ID | Scenario | Complexity | Responsible Tester | Date of Execution(Can be past, present or future date) | Actual Result | Status(Pass/Fail/Blocked/Not Executed) | Defect ID - Brief Description | Severity | Status | Notes
Admin Login Module | TC_INV_A1 | Admin ID & Password with Special Characters | Medium | Parth Patel | 2024-01-08 | SORRY! Invalid username/password, please try again | Passed
| TC_INV_A2 | Admin ID & Password with MAX+1 Characters | Medium | Parth Patel | 2024-01-08 | SORRY! Invalid username/password, please try again | Passed
Admin Login Module | TC_INV_A3 | Empty Admin ID and Password | Medium | Parth Patel | 2024-01-08 | SORRY! Invalid username/password, please try again | Passed
Admin - Add Route Module | TC_INV_A4 | Fields with Max Characters + 1 | Medium | Parth Patel | 2024-01-08 | Error Message | Passed
Admin - Add Route Module | TC_INV_A5 | Fields with Min Characters - 1 | Medium | Parth Patel | 2024-01-08 | Fields are mandatory | Passed
Admin - Add Route Module | TC_INV_A6 | Fields with Special Characters | Medium | Parth Patel | 2024-01-08 | Error Message | Passed
Admin - Add Route Module | TC_INV_A7 | Null Fields | Medium | Parth Patel | 2024-01-08 | Error Message | Passed
Admin - Add Route Module | TC_INV_A8 | Negative Fare | Complex | Parth Patel | 2024-01-08 | Route added Successfully | Failed | DF_001: The error message for a negative fare did not appear, and the system accepted the negative fare, allowing the route to be added successfully. | High | Open | The system needs to be updated to correctly handle and reject negative fare entries with an appropriate error message.
Admin - Add Route Module | TC_INV_A9 | Alphabetical Characters in Fare | Medium | Parth Patel | 2024-01-08 | Error Message | Passed
Admin - Add Route Module | TC_INV_A10 | Duplicate Entries | Complex | Parth Patel | 2024-01-08 | Route added Successfully | Failed | DF_002: The error message for a duplicate entry did not appear, and the system accepted the duplicate entry, allowing the route to be added successfully. | High | Open | The system needs to be updated to correctly handle and reject duplicate entries with an appropriate error message.
Admin - Delete Route Module | TC_INV_A11 | Invalid RouteID Format | Medium | Parth Patel | 2024-01-08 | Error in deletion..please try again | Passed
Admin - Delete Route Module | TC_INV_A12 | Special Characters in RouteID | Medium | Parth Patel | 2024-01-08 | Error in deletion..please try again | Passed
Admin - Delete Route Module | TC_INV_A13 | Non-Existing RouteID | Medium | Parth Patel | 2024-01-08 | Error in deletion..please try again | Passed
Admin - Delete Route Module | TC_INV_A14 | RouteID as Numeric Value Below Valid Range | Medium | Parth Patel | 2024-01-08 | Error in deletion..please try again | Passed
Admin - Add New Travel Module | TC_INV_A15 | All Fields with Exceeding Length | Medium | Parth Patel | 2024-01-08 | Error Message | Passed
Admin - Add New Travel Module | TC_INV_A16 | All Fields with Special Characters | Medium | Parth Patel | 2024-01-08 | Error Message | Passed
Admin - Add New Travel Module | TC_INV_A17 | All Fields with Empty Values | Medium | Parth Patel | 2024-01-08 | Error Message | Passed
Admin - Add New Travel Module | TC_INV_A18 | All Fields with Invalid Formats | Medium | Parth Patel | 2024-01-08 | Error Message | Passed
Admin - Add New Travel Module | TC_INV_A19 | All Fields with Too Short Inputs | Medium | Parth Patel | 2024-01-08 | Error Message | Passed
Admin - Add New Travel Module | TC_INV_A20 | All Fields with Numerical Input | Medium | Parth Patel | 2024-01-08 | Error Message | Passed
Admin - Add New Travel Module | TC_INV_A21 | All Fields with Duplicate Data | Complex | Parth Patel | 2024-01-08 | Travels added Successfully | Failed | DF_003: The error message for a duplicate data did not appear, and the system accepted the duplicate data, allowing the travel to be added successfully. | High | Open | The system needs to be updated to correctly handle and reject duplicate data entries with an appropriate error message.
Admin - Add New Travel Module | TC_INV_A22 | All Fields with Alphanumeric Mix | Medium | Parth Patel | 2024-01-08 | Error Message | Passed
Admin - Delete Travel Module | TC_INV_A23 | Invalid TravelsID Format | Medium | Parth Patel | 2024-01-08 | Error in deletion..please try again | Passed
Admin - Delete Travel Module | TC_INV_A24 | Special Characters in TravelsID | Medium | Parth Patel | 2024-01-08 | Error in deletion..please try again | Passed
Admin - Delete Travel Module | TC_INV_A25 | Non-Existing TravelsID | Medium | Parth Patel | 2024-01-08 | Error in deletion..please try again | Passed
Admin - Delete Travel Module | TC_INV_A26 | TravelsID as Numeric Value Below Valid Range | Medium | Parth Patel | 2024-01-08 | Error in deletion..please try again | Passed
User Login Module | TC_INV_U1 | User ID & Password with Special Characters | Medium | Parth Patel | 2024-01-08 | SORRY! Invalid username/password, please try again | Passed
User Login Module | TC_INV_U2 | User ID & Password with MAX+1 Characters | Medium | Parth Patel | 2024-01-08 | SORRY! Invalid username/password, please try again | Passed
User Login Module | TC_INV_U3 | Empty User ID and Password | Medium | Parth Patel | 2024-01-08 | SORRY! Invalid username/password, please try again | Passed
User - Book Ticket Module | TC_INV_U4 | Fields with Special Characters | Medium | Parth Patel | 2024-01-08 | HTTP Status 500 – Internal Server Error | Passed
User - Book Ticket Module | TC_INV_U5 | Fields with Empty Values | Medium | Parth Patel | 2024-01-08 | HTTP Status 500 – Internal Server Error | Passed
User - Book Ticket Module | TC_INV_U6 | Fields with Too Short Inputs | Complex | Parth Patel | 2024-01-08 | No Busses available.Please refine your search and try again | Passed
User - Book Ticket Module | TC_INV_U7 | Fields with Exceeding Length | Complex | Parth Patel | 2024-01-08 | Blank Screen | Failed | DF_004: The error message for a Fields with Exceeding Length did not appear, and the system gave blank scrren. | High | Open | The system needs to be updated to correctly handle and reject Fields with Exceeding Length with an appropriate error message.
User - Book Ticket Module | TC_INV_U8 | Fields with Alphanumeric Mix | Medium | Parth Patel | 2024-02-08 | HTTP Status 500 – Internal Server Error | Passed
User - Book Ticket Module | TC_INV_U9 | Fields with Random Special Characters and Symbols | Medium | Parth Patel | 2024-02-08 | HTTP Status 500 – Internal Server Error | Passed
User - Book Ticket Module | TC_INV_U10 | Fields with Incorrect Format | Complex | Parth Patel | 2024-02-08 | No Busses available.Please refine your search and try again | Passed
User - Customer Info Module | TC_INV_U11 | Fields with Special Characters | Medium | Parth Patel | 2024-02-08 | Alert box showing error in fields | Passed
User - Customer Info Module | TC_INV_U12 | Fields with Empty Values | Medium | Parth Patel | 2024-02-08 | Alert box showing all the fields are mandtory | Passed
User - Customer Info Module | TC_INV_U13 | Fields with Too Short Inputs | Medium | Parth Patel | 2024-02-08 | Alert box showing error in fields | Passed
User - Customer Info Module | TC_INV_U14 | Fields with Exceeding Length | Medium | Parth Patel | 2024-02-08 | Error message | Passed
User - Customer Info Module | TC_INV_U15 | Fields with Alphanumeric Mix | Medium | Parth Patel | 2024-02-08 | Error message | Passed
User - Customer Info Module | TC_INV_U16 | Fields with Random Special Characters and Symbols | Medium | Parth Patel | 2024-02-08 | Error message | Passed
User - Customer Info Module | TC_INV_U17 | Field with Incorrect Email Format | Medium | Parth Patel | 2024-02-08 | Please enter valid email for email | Passed
User - Customer Info Module | TC_INV_U18 | Fields with Duplicate Data | Medium | Parth Patel | 2024-02-08 | Error | Passed
User - Payment Module | TC_INV_U19 | Fields with Special Characters | Medium | Parth Patel | 2024-02-08 | Please enter valid Card Number | Passed
User - Payment Module | TC_INV_U20 | Fields with Empty Values | Medium | Parth Patel | 2024-02-08 | Bank Name is mandatory | Passed
User - Payment Module | TC_INV_U21 | Fields with Too Short Inputs | Medium | Parth Patel | 2024-02-08 | Please enter valid Card Number | Passed
User - Payment Module | TC_INV_U22 | Fields with Exceeding Length | Medium | Parth Patel | 2024-02-08 | Please enter valid Card Number | Passed
User - Payment Module | TC_INV_U23 | Fields with Alphanumeric Mix | Medium | Parth Patel | 2024-02-08 | Please enter valid Card Number | Passed
User - Payment Module | TC_INV_U24 | Fields with Random Special Characters and Symbols | Medium | Parth Patel | 2024-02-08 | Please enter valid Card Number | Passed
User - Payment Module | TC_INV_U25 | Fields with Incorrect Format | Medium | Parth Patel | 2024-02-08 | Please enter valid Card Number | Passed
User - Cancel Ticket Module | TC_INV_U26 | Field with Special Characters | Medium | Parth Patel | 2024-02-08 | No tickets found.Please provide valid Ticket Id | Passed
User - Cancel Ticket Module | TC_INV_U27 | Field with Empty Value | Medium | Parth Patel | 2024-02-08 | TicketId is mandatory | Passed
User - Cancel Ticket Module | TC_INV_U28 | Field with Too Short Input | Medium | Parth Patel | 2024-02-08 | No tickets found.Please provide valid Ticket Id | Passed
User - Cancel Ticket Module | TC_INV_U29 | Field with Exceeding Length | Medium | Parth Patel | 2024-02-08 | No tickets found.Please provide valid Ticket Id | Passed
User - Cancel Ticket Module | TC_INV_U30 | Field with Alphanumeric Mix | Medium | Parth Patel | 2024-02-08 | No tickets found.Please provide valid Ticket Id | Passed
User - Cancel Ticket Module | TC_INV_U31 | Field with Random Special Characters and Symbols | Medium | Parth Patel | 2024-02-08 | No tickets found.Please provide valid Ticket Id | Passed
User - Give Feedback Module | TC_INV_U32 | Fields with Special Characters | Complex | Parth Patel | 2024-02-08 | Your Feedback submitted successfully! Thanks for providing your feedback. | Failed | DF_005: The error message for Fields with Special Characters did not appear, and the system accepted the Fields with Special Characters, allowing the Feedback to be Submitted successfully. | High | Open | The system needs to be updated to correctly handle and reject Fields with Special Characters with an appropriate error message.
User - Give Feedback Module | TC_INV_U33 | Fields with Empty Values | Medium | Parth Patel | 2024-02-08 | Alert box saying error | Passed
User - Give Feedback Module | TC_INV_U34 | Email Field with Too Short Input | Complex | Parth Patel | 2024-02-08 | Your Feedback submitted successfully! Thanks for providing your feedback. | Failed | DF_006: The error message for a Email Field with Too Short Input did not appear, and the system accepted the short input, allowing the Feedback to be Submitted successfully. | High | Open | The system needs to be updated to correctly handle and reject short data entries with an appropriate error message.
User - Give Feedback Module | TC_INV_U35 | Feedback Field with Exceeding Length | Medium | Parth Patel | 2024-02-08 | com.mysql.cj.jdbc.exceptions.MysqlDataTruncation: Data truncation: Data too long for column 'UserID' at row 1 | Passed
User - Give Feedback Module | TC_INV_U36 | Email Field with Incorrect Format | Complex | Parth Patel | 2024-02-08 | Your Feedback submitted successfully! Thanks for providing your feedback. | Failed | DF_007: The error message for a Email Field with Incorrect Format did not appear, and the system accepted the email Field, allowing the Feedback to be Submitted successfully. | High | Open | The system needs to be updated to correctly handle and reject incorrect format with an appropriate error message.

## Valid Test Cases Execution
Module | Test Case ID | Scenario | Complexity | Responsible Tester | Date of Execution(Can be past, present or future date) | Actual Result | Status(Pass/Fail/Blocked/Not Executed) | Defect ID - Brief Description | Severity | Status | Notes
Admin Login Module | TC_VAL_A1 | Admin Login | Medium | Parth Patel | 2024-02-08 | LogIn successful. | Passed
Admin Login Module | TC_VAL_A2 | Clear Button | Medium | Parth Patel | 2024-02-08 | Fields were cleared | Passed
Admin - Add Route Module | TC_VAL_A3 | Add Route with minimum values | Medium | Parth Patel | 2024-02-08 | Route added Successfully | Passed
Admin - Add Route Module | TC_VAL_A4 | Add Route | Medium | Parth Patel | 2024-02-08 | Route added Successfully | Passed
Admin - Add Route Module | TC_VAL_A5 | Add Route with Max values | Medium | Parth Patel | 2024-03-08 | Route added Successfully | Passed
Admin - Add Route Module | TC_VAL_A6 | Submit Button | Medium | Parth Patel | 2024-03-08 | Route added Successfully | Passed
Admin - Add Route Module | TC_VAL_A7 | Clear Button | Medium | Parth Patel | 2024-03-08 | Fields were cleared. | Passed
Admin - Delete Route Module | TC_VAL_A8 | Delete Route | Medium | Parth Patel | 2024-03-08 | Route deleted successfully | Passed
Admin - View Route Module | TC_VAL_A9 | Admin view routes | Medium | Parth Patel | 2024-03-08 | All data properly displayed | Passed
Admin - Add Pickup Point Module | TC_VAL_A10 | Add pickup point with minimum values | Medium | Parth Patel | 2024-03-08 | Pickup point added Successfully | Passed
Admin - Add Pickup Point Module | TC_VAL_A11 | Add pickup point | Medium | Parth Patel | 2024-03-08 | Pickup point added Successfully | Passed
Admin - Add Pickup Point Module | TC_VAL_A12 | Add pickup point with maximum values. | Medium | Parth Patel | 2024-03-08 | Pickup point added Successfully | Passed
Admin - Add New Travel Module | TC_VAL_A13 | Add New Travel with minimum value. | Medium | Parth Patel | 2024-03-08 | Travels added Successfully | Passed
Admin - Add New Travel Module | TC_VAL_A14 | Add New Travel | Medium | Parth Patel | 2024-03-08 | Travels added Successfully | Passed
Admin - Add New Travel Module | TC_VAL_A15 | Add New Travel with maximum values. | Medium | Parth Patel | 2024-03-08 | Travels added Successfully | Passed
Admin - Add New Travel Module | TC_VAL_A16 | Submit Button | Medium | Parth Patel | 2024-03-08 | Travels added Successfully | Passed
Admin - Add New Travel Module | TC_VAL_A17 | Clear Button | Medium | Parth Patel | 2024-03-08 | All the fields were cleared. | Passed
Admin - Delete Travel Module | TC_VAL_A18 | Delete Travel | Medium | Parth Patel | 2024-03-08 | Travel deleted successfully | Passed
Admin - Logout Module | TC_VAL_A19 | Admin Log Out | Medium | Parth Patel | 2024-03-08 | Logout Successful | Passed
User - Login Module | TC_VAL_U1 | User Log In | Medium | Parth Patel | 2024-03-08 | Displayed home page. | Passed
User - Login Module | TC_VAL_U2 | Clear Button | Medium | Parth Patel | 2024-03-08 | Cleared all fields | Passed
User - View Route Module | TC_VAL_U3 | View Routes | Medium | Parth Patel | 2024-03-08 | Routes Displayed | Passed
User - View Pickup Point Module | TC_VAL_U4 | View PickUp point | Medium | Parth Patel | 2024-03-08 | List of pick up points displayed | Passed
User - Book Tickets Module | TC_VAL_U5 | Check Availability with min values | Medium | Parth Patel | 2024-03-08 | Available bus options displayed | Passed
User - Book Tickets Module | TC_VAL_U6 | Check Availability Button | Medium | Parth Patel | 2024-03-08 | Available bus options displayed | Passed
User - Book Tickets Module | TC_VAL_U7 | Check Availability with max values | Medium | Parth Patel | 2024-03-08 | Available bus options displayed | Passed
User - Book Tickets Module | TC_VAL_U8 | Bus Selection | Medium | Parth Patel | 2024-03-08 | Bus selection page opened | Passed
User - Book Tickets Module | TC_VAL_U9 | Seat Selection | Medium | Parth Patel | 2024-03-08 | Seat selection page opened | Passed
User - Book Tickets Module | TC_VAL_U10 | Customer Information with minimum values | Medium | Parth Patel | 2024-03-08 | Customer info saved successfully | Passed
User - Book Tickets Module | TC_VAL_U11 | Customer Information | Medium | Parth Patel | 2024-03-08 | Customer info saved successfully | Passed
User - Book Tickets Module | TC_VAL_U12 | Customer Information with maximum values | Medium | Parth Patel | 2024-03-08 | Customer info saved successfully | Passed
User - Book Tickets Module | TC_VAL_U13 | Payment with minimum values | Medium | Parth Patel | 2024-03-08 | Payment details saved successfully | Passed
User - Book Tickets Module | TC_VAL_U14 | Payment | Medium | Parth Patel | 2024-03-08 | Payment details saved successfully | Passed
User - Cancel Tickets Module | TC_VAL_U15 | Cancel Ticket Button | Medium | Parth Patel | 2024-03-08 | Your ticket has been successfully cancelled. | Passed
User - Give Feedback Module | TC_VAL_U16 | Give Feedback with maximum email fields | Medium | Parth Patel | 2024-03-08 | Your Feedback submitted successfully! Thanks for providing your feedback. | Passed
User - Give Feedback Module | TC_VAL_U17 | Give Feedback | Medium | Parth Patel | 2024-03-08 | Your Feedback submitted successfully! Thanks for providing your feedback. | Passed
User - Give Feedback Module | TC_VAL_U18 | Clear Button | Medium | Parth Patel | 2024-03-08 | cleared all data from field | Passed

## Defect Report
DEFECT TRACKING LOG
Project Name | TravelApp
Program Manager | Shrijy Atodaria
Project Manager | Vijul Vyas
Defect No: | Date Created | Created By | Defect Description | Steps to reproduce | Label | PM Process | LifeCycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status
DF_001 | 2024-01-08 | Parth Patel | The error message for a negative fare did not appear, and the system accepted the negative fare, allowing the route to be added successfully. | 1. Launch TravelAPP into Chrome broswer 2. Navigate to the "Add New Route" section. 3. Provide the details: From: London To: Windsor Travels Id: Travel123 Bus Id: Bus123 Departure: 12:00 Arrival: 14:00 Fare: -100 (negative value) Journey Date: 2024-07-14 3. Click On Submit button | Add Route - Negative Fare Defect | Controlling | Execution | High | Rutvik Patel | 2024-01-08 | 1-2 Hours | Open
DF_002 | 2024-01-08 | Parth Patel | The error message for a duplicate entry did not appear, and the system accepted the duplicate entry, allowing the route to be added successfully. | 1. Launch TravelAPP into Chrome broswer 2. Navigate to the "Add New Route" section. 3. Provide the details: From: London To: Berry Travels Id: Travel123 Bus Id: Bus123 Departure: 12:00 Arrival: 14:00 Fare: 100 Journey Date: 2024-07-14 3. Click On Submit button | Add Route - Duplicate Entry | Controlling | Execution | High | Rutvik Patel | 2024-01-08 | 1-1.5 Hours | Open
DF_003 | 2024-01-08 | Parth Patel | The error message for a duplicate data did not appear, and the system accepted the duplicate data, allowing the travel to be added successfully. | 1. Launch TravelAPP into Chrome broswer 2. Navigate to the "Add New Travel" section. 3. Provide the details: Travel Name: DuplicateTravel (Duplicate value) Location: DuplicateLocation (Duplicate value) Address: DuplicateAddress (Duplicate value) Agent Name: DuplicateAgent (Duplicate value) Phone Number: 9999999999 (Duplicate value) 3. Click On Submit button | Add New Travel Module - All Fields with Duplicate Data | Controlling | Execution | High | Rutvik Patel | 2024-01-08 | 1-1.5 Hours | Open
DF_004 | 2024-01-08 | Parth Patel | The error message for a Fields with Exceeding Length did not appear, and the system gave blank scrren. | 1. Launch TravelAPP into Chrome broswer 2. Provide the details: User ID: capstone Password: info6068 3. Go to book ticket page 4. Provide the details: Journey Date: 12/31/20222222222222 (Exceeds expected date length) No. of Passengers: 12345678901234567890 (Exceeds expected passenger count length) 5. Click On Check Availibility button " | Book Ticket Module - Fields with Exceeding Length | Executing | Execution | High | Rutvik Patel | 2024-01-08 | 2-3 Hours | Open
DF_005 | 2024-02-08 | Parth Patel | The error message for Fields with Special Characters did not appear, and the system accepted the Fields with Special Characters, allowing the Feedback to be Submitted successfully. | 1. Launch TravelApp into Chrome browser. 2. Provide the login details: User ID: capstone Password: info6068 3. Go to Give Feedback page. 4. Provide the details: Your Email ID: p@*#thpa^tel@gmail.com Feedback: One^of%the#best!experience 5. Click on Submit Feedback Button. | Give Feedback Module - Fields with Special Characters | Executing | Execution | High | Rutvik Patel | 2024-02-08 | 4-5 Hours | Open
DF_006 | 2024-02-08 | Parth Patel | The error message for a Email Field with Too Short Input did not appear, and the system accepted the short input, allowing the Feedback to be Submitted successfully. | 1. Launch TravelApp into Chrome browser. 2. Provide the login details: User ID: capstone Password: info6068 3. Go to Give Feedback page. 4. Provide the details: Your Email ID: a@b.c (Too short to be valid) Feedback: G (Too Short) 5. Click on Submit Feedback Button. | Give Feedback Module - Email Field with Too Short Input | Executing | Execution | High | Rutvik Patel | 2024-02-08 | 1 hour | Open
DF_007 | 2024-02-08 | Parth Patel | The error message for a Email Field with Incorrect Format did not appear, and the system accepted the email Field, allowing the Feedback to be Submitted successfully. | 1. Launch TravelApp into Chrome browser. 2. Provide the login details: User ID: capstone Password: info6068 3. Go to Give Feedback page. 4. Provide the details: Your Email ID: parth@gmail (Missing domain) Feedback: Great service 5. Click on Submit Feedback Button. | Give Feedback Module - Email Field with Incorrect Format | Controlling | Execution | High | Rutvik Patel | 2024-02-08 | 2 hour | Open

## Test Cases By Business Area
Test case execution
Functional Area | Total number of test cases | Number of test cases executed | # of passed test cases | Not run | # of failed test cases | Pending clarification | % of test cases executed | % of test cases passed | % of test cases Failed
Admin Login Module | 5 | 5 | 5 | 0 | 0 | 0 | 100% | 100% | 0%
Admin - Add Route Module | 12 | 12 | 10 | 0 | 2 | 0 | 100% | 83.3333 | 16.6667
Admin - Delete Route Module | 5 | 5 | 5 | 0 | 0 | 0 | 100% | 100% | 0%
Admin - Add New Travel Module | 13 | 13 | 12 | 0 | 1 | 0 | 100% | 92.3077 | 7.6923
Admin - Delete Travel Module | 5 | 5 | 5 | 0 | 0 | 0 | 100% | 100% | 0%
User Login Module | 5 | 5 | 5 | 0 | 0 | 0 | 100% | 100% | 0%
User - Book Ticket Module | 17 | 17 | 16 | 0 | 1 | 0 | 100% | 94.1176 | 5.8824
User - Customer Info Module | 8 | 8 | 8 | 0 | 0 | 0 | 100% | 100% | 0%
User - Payment Module | 7 | 7 | 7 | 0 | 0 | 0 | 100% | 100% | 0%
User - Cancel Ticket Module | 7 | 7 | 7 | 0 | 0 | 0 | 100% | 100% | 0%
User - Give Feedback Module | 8 | 8 | 5 | 0 | 3 | 0 | 100% | 62.5 | 37.5
Admin - View Route Module | 1 | 1 | 1 | 0 | 0 | 0 | 100% | 100% | 0%
Admin - Add Pickup Point Module | 3 | 3 | 3 | 0 | 0 | 0 | 100% | 100% | 0%
Admin - Logout Module | 1 | 1 | 1 | 0 | 0 | 0 | 100% | 100% | 0%
User - View Route Module | 1 | 1 | 1 | 0 | 0 | 0 | 100% | 100% | 0%
User - View Pickup Point Module | 1 | 1 | 1 | 0 | 0 | 0 | 100% | 100% | 0%
Defects
Functional area | Critical | High | Medium | Low
Admin - Add Route Module | 2 | 0 | 10 | 0
Admin - Add New Travel Module | 1 | 0 | 12 | 0
User - Book Ticket Module | 16 | 0 | 1 | 0
User - Give Feedback Module | 5 | 0 | 3 | 0